## validate
| Initiating | Planning | Executing | Monitoring and Controlling | Closing
Integration
Scope | x
x
x
x
x
x
x
| horizontally forward | vertically forward | identify all the x's
| horizontally backward | vertically backward | how many in each column

## check
| Initiating | Planning | Executing | Monitoring and Controlling | Closing
Integration | Develop Project Charter | Develop Project Management Plan | Direct and Manage Project Execution | Monitor and Control Project Work, Perform Integrated Change Control | Close Project or Phase
Scope | x | Collect Requirements, Define Scope, Create WBS | x | Verify Scope, Control Scope | x
Time | x | Define Activities, Sequence Activities, Estimate Activity Resources, Estimate Activity Durations, Develop Schedule | x | Control Schedule | x
Cost | x | Estimate Costs, Determine Budget | x | Control Costs | x
Quality | x | Plan Quality | Perform Quality Assurance | Perform Quality Control | x
Human Resource | x | Develop Human Resource Plan | Acquire Project Team, Develop Project Team, Manage Project Team | x | x
Communications | Identify Stakeholders | Plan Communications | Distribute Information, Manage Stakeholder Expectations | Report Performance | x
Risk | x | Plan Risk Management, Identify Risks, Perform Qualitative Risk Analysis, Perform Quantitative Risk Analysis, Plan Risk Responses | x | Monitor and Control Risks | x
Procurement | x | Plan Procurements | Conduct Procurements | Administer Procurements | Close Procurements